## Template Guide
Risk Assessment Template
Guide - How to use this Template
1 | On the "1. Assess Risks" sheet, fill all the blue cells with your project information, and your assessment of the risk
on your specific project, using the zero to 4 guidance. Fill in all the cells. If for some reason
a risk statement is not applicable to your project, assign a zero.
2
3
4

## 1. Assess Risks
Risk Assessment Template
| 1. ENTER PROJECT DETAILS: |  | 2. USE RATINGS TO ANSWER EACH RISK QUESTION:
| Project: | Project ABC | 0 - N/A
| Date of Assessment: |  | 1 - Small risk, no PII, Public
| Planned Target Month: |  | 2 - Moderate risk, Non sensit PII, Internal, existing vendor
| Template Completed by (who): | John Doe | 3 - Significant risk, Restricted, Sensitive PII
4 - High risk, HiR, InfoSec, IP, new vendor
Risk # | FOR EACH QUESTION, ASK OF YOURSELF/THE TEAM - "WHAT IS THE RISK TO THE START-UP RESULT FROM THIS FACTOR?" |  |  | Level of Risk
1 | Country
1.1 | China |  |  | 4 | Ensure Privacy, Information Security and Legal documentation are completed and approved.
1.2 | Europe/European Union |  |  | 4 | Ensure Privacy, Information Security and Legal documentation are completed and approved.
1.3 | Africa/Mid East |  |  | 0 | Ensure Privacy, Information Security and Legal documentation are completed and approved.
1.4 | Latin America |  |  | 0 | Ensure Privacy, Information Security and Legal documentation are completed and approved.
2 | Primary Objective
2.1 | New technology introduced |  |  | 4 | Review for Record Lifecycle Management, Information Security and Operational Validation.
2.2 | A new or significant change to an application that provides regulated support |  |  | 0 | Review for Record Lifecycle Management, Information Security and Regulatory Validation.
2.3 | New or Change in Cloud Computing |  |  | 4 | Complete Cloud Vetting Assesment.
2.4 | New business geography (new for this application/project; new for the Company) |  |  | 0 | Review legal risks and local laws vs. retention schedule.
2.5 | New--or--major upgrade to an IT Application |  |  | 0 | Ensure all current standards and policies are followed.
3 | ?
3.1
3.2
3.3
3.4
3.5
4 | 4
4.1
4.2
4.3
4.4
4.5
5 | 5
5.1
5.2
5.3
5.4
5.5
6 | 6
6.1
6.2
6.3
6.4
6.5
7 | 7
7.1
7.2
7.3
7.4
7.5
7.6
8 | 8
8.1
8.2
8.3
8.4
9 | 9
9.1
9.2
9.3
9.4
9.5
9.6
10 | 10
10.1
10.2
11 | 11
11.1
11.2
11.3
12 | 12
12.1
12.2
12.3
Note on C7: Paul Gaskell: Record all participants who took part.
Note on A52: Paul Gaskell: In the case of Acceptance Testing being not applicable, or partly applicable (e.g. a Making system being constructed on site) - if you believe there is no risk to the Start-Up result from the subject of the question, simply answer with a zero
Note on B52: Paul Gaskell: In the case of Acceptance Testing being not applicable, or partly applicable (e.g. a Making system being constructed on site) - if you believe there is no risk to the Start-Up result from the subject of the question, simply answer with a zero
Note on E53: Paul Gaskell: In the case of Acceptance Testing being not applicable, or partly applicable (e.g. a Making system being constructed on site) - if you believe there is no risk to the Start-Up result from the subject of the question, simply answer with a zero
Note on E54: Paul Gaskell: In the case of Acceptance Testing being not applicable, or partly applicable (e.g. a Making system being constructed on site) - if you believe there is no risk to the Start-Up result from the subject of the question, simply answer with a zero
Note on E55: Paul Gaskell: In the case of Acceptance Testing being not applicable, or partly applicable (e.g. a Making system being constructed on site) - if you believe there is no risk to the Start-Up result from the subject of the question, simply answer with a zero
Note on E56: Paul Gaskell: In the case of Acceptance Testing being not applicable, or partly applicable (e.g. a Making system being constructed on site) - if you believe there is no risk to the Start-Up result from the subject of the question, simply answer with a zero

## 2. Output - summary
Risk Assessment Template
| 0 - N/A |  |  | Project: | Project ABC
| 1 - Small risk, no PII, Public |  |  | Date of Assessment: | 0
| 2 - Moderate risk, Non sensit PII, Internal, existing vendor |  |  | Planned Target Month: | 0
| 3 - Significant risk, Restricted, Sensitive PII |  |  | Template Completed by (who): | John Doe
4 - High risk, HiR, InfoSec, IP, new vendor
| Average Score by Risk Area: |  |  |  | High Score = High Risk Area!
1 | Country | 2 | 0.14136 | 0.85864
2 | Primary Objective | 1.6 | 0.088848 | 0.91115
3 | ? | #DIV/0! | #DIV/0! | #DIV/0!
4 | 4 | #DIV/0! | #DIV/0! | #DIV/0!
5 | 5 | #DIV/0! | #DIV/0! | #DIV/0!
6 | 6 | #DIV/0! | #DIV/0! | #DIV/0!
7 | 7 | #DIV/0! | #DIV/0! | #DIV/0!
8 | 8 | #DIV/0! | #DIV/0! | #DIV/0!
9 | 9 | #DIV/0! | #DIV/0! | #DIV/0!
10 | 10 | #DIV/0! | #DIV/0! | #DIV/0!
11 | 11 | #DIV/0! | #DIV/0! | #DIV/0!
12 | 12 | #DIV/0! | #DIV/0! | #DIV/0!
Overall Estimated Probability of mitigating risks
#DIV/0!
| Number of Areas rated 4 - | 4
| Number of Areas rated 3 - | 0
| Number of Areas rated 2 - | 0
| Number of Areas rated 1 - | 0
| Number of Areas rated 0 - | 5
NOT ALL 53 QUESTIONS ANSWERED!!

## 3. Output - indicated actions
Risk Assessment Template
|  |  |  | Project: | Project ABC
|  |  |  | Date of Assessment: | 0
|  |  |  | Planned Target Month: | 0
|  |  |  | Template Completed by (who): | John Doe
|  |  | 1.5 | Enter action limit for Individual Risk Ratings
|  |  | 2.5 | Enter action limit for Group Risk Ratings (not always needed)
Risk # |  | Individual Rating | Group Rating | Indicated Action (if any)
1.1 | China | 4 | 2 | Ensure Privacy, Information Security and Legal documentation are completed and approved.
1.2 | Europe/European Union | 4 | 2 | Ensure Privacy, Information Security and Legal documentation are completed and approved.
1.3 | Africa/Mid East | 0 | 2
1.4 | Latin America | 0 | 2
2.1 | New technology introduced | 4 | 1.6 | Review for Record Lifecycle Management, Information Security and Operational Validation.
2.2 | A new or significant change to an application that provides regulated support | 0 | 1.6
2.3 | New or Change in Cloud Computing | 4 | 1.6 | Complete Cloud Vetting Assesment.
2.4 | New business geography (new for this application/project; new for the Company) | 0 | 1.6
2.5 | New--or--major upgrade to an IT Application | 0 | 1.6
3.1 | 0 | 0 | #DIV/0! | #DIV/0!
3.2 | 0 | 0 | #DIV/0! | #DIV/0!
3.3 | 0 | 0 | #DIV/0! | #DIV/0!
3.4 | 0 | 0 | #DIV/0! | #DIV/0!
3.5 | 0 | 0 | #DIV/0! | #DIV/0!
4.1 | 0 | 0 | #DIV/0! | #DIV/0!
4.2 | 0 | 0 | #DIV/0! | #DIV/0!
4.3 | 0 | 0 | #DIV/0! | #DIV/0!
4.4 | 0 | 0 | #DIV/0! | #DIV/0!
4.5 | 0 | 0 | #DIV/0! | #DIV/0!
5.1 | 0 | 0 | #DIV/0! | #DIV/0!
5.3 | 0 | 0 | #DIV/0! | #DIV/0!
5.4 | 0 | 0 | #DIV/0! | #DIV/0!
5.5 | 0 | 0 | #DIV/0! | #DIV/0!
6.1 | 0 | 0 | #DIV/0! | #DIV/0!
6.2 | 0 | 0 | #DIV/0! | #DIV/0!
6.3 | 0 | 0 | #DIV/0! | #DIV/0!
6.4 | 0 | 0 | #DIV/0! | #DIV/0!
6.5 | 0 | 0 | #DIV/0! | #DIV/0!
7.1 | 0 | 0 | #DIV/0! | #DIV/0!
7.2 | 0 | 0 | #DIV/0! | #DIV/0!
7.3 | 0 | 0 | #DIV/0! | #DIV/0!
7.4 | 0 | 0 | #DIV/0! | #DIV/0!
7.5 | 0 | 0 | #DIV/0! | #DIV/0!
7.6 | 0 | 0 | #DIV/0! | #DIV/0!
8.1 | 0 | 0 | #DIV/0! | #DIV/0!
8.2 | 0 | 0 | #DIV/0! | #DIV/0!
8.3 | 0 | 0 | #DIV/0! | #DIV/0!
8.4 | 0 | 0 | #DIV/0! | #DIV/0!
9.1 | 0 | 0 | #DIV/0! | #DIV/0!
9.2 | 0 | 0 | #DIV/0! | #DIV/0!
9.3 | 0 | 0 | #DIV/0! | #DIV/0!
9.4 | 0 | 0 | #DIV/0! | #DIV/0!
9.5 | 0 | 0 | #DIV/0! | #DIV/0!
9.6 | 0 | 0 | #DIV/0! | #DIV/0!
10.1 | 0 | 0 | #DIV/0! | #DIV/0!
10.2 | 0 | 0 | #DIV/0! | #DIV/0!
11.1 | 0 | 0 | #DIV/0! | #DIV/0!
11.2 | 0 | 0 | #DIV/0! | #DIV/0!
11.3 | 0 | 0 | #DIV/0! | #DIV/0!
12.1 | 0 | 0 | #DIV/0! | #DIV/0!
12.2 | 0 | 0 | #DIV/0! | #DIV/0!
12.3 |  | 0 | #DIV/0! | #DIV/0!

## Calculation
Risk Assessment Template
Calculation sheet Only - No User Input Required Here
Overall Probability Indicator Calculation
Based on the ratings - |  | 0 - N/A
1 - Small risk, no PII, Public
2 - Moderate risk, Non sensit PII, Internal, existing vendor
3 - Significant risk, Restricted, Sensitive PII
4 - High risk, HiR, InfoSec, IP, new vendor
Create a probability function:
| Rating | Risk of this factor causing miss | (i.e.)
| 0 | 0.005 | 0.5%
| 1 | 0.025 | 2.5%
| 2 | 0.15 | 15%
| 3 | 0.4 | 40%
| 4 | 0.8 | 80%
Equation on graph shows best fit (power) trend line automatically.
Write values from this trend line equation here
|  |  | P(x) = | 0.004 | R^ | 3.245 | Where R = (Rating + 1)
Then take the risk rating for each individual statement, and convert to a risk from this equation.
Finally, take the product of (1-risks) to establish an overall likelihood of achieving goal